## CAPA
Spreadsheet no: ES.CSV.010 CAPA Spreadsheet Owner: Omair Sattar Ref. SOP: ES.SOP.044 |  |  |  |  | QMS DATA CAPA, Version 1.1
CAPA Reference | Date Logged | Logged By | QA RP | Assignable Cause | Category (Minor / Major / Critical) | Actions | Person Assigned | Target date | Date Closed | Days Open | Status | Wet Ink Copy Filed (Y/N) | Location | Comments
CAPA.2026.001 | 2026-01-02 | MR | MA | DEV.2025.039 - Batch of duloxetine rejected due to excessive foaming | Major | Reassess formulation and usage of new brand if required. | MA | 2026-02-05 | 2026-02-03 | 32 | Complete | Y | Closed CAPA File
CAPA.2026.002/A | 2026-01-19 | AHA | MA | DEV.2025.035 - Batch of Tranexamic Acid 500 mg/5 ml Solution rejected due to incorrect excipient added during final volume check | Minor | Reinforce fit-to-work requirements through targeted awareness brief for all production staff emphasising the expectation to stop work and escalate to management if unwell or unable to safely perform GMP activities. | MA | 2026-01-23 | 2026-01-23 | 4 | Complete | Y | Closed CAPA File
CAPA.2026.002/B | 2026-01-19 | AHA | MA | DEV.2025.035 - Batch of Tranexamic Acid 500 mg/5 ml Solution rejected due to incorrect excipient added during final volume check | Minor | Update ES.SOP.191 and ES.SOP.013 to explicitly prohibit preparation of materials prior to checker presence and enforce a strict “verify before add” pause point. Also update the SOP to state that the volume checker must witness the volume being made up prior to signing for volume check. | MA | 2026-02-09 | 2026-02-03 | 15 | Complete | Y | Closed CAPA File
CAPA.2026.002/C | 2026-01-19 | AHA | MA | DEV.2025.035 - Batch of Tranexamic Acid 500 mg/5 ml Solution rejected due to incorrect excipient added during final volume check | Minor | Conduct Awareness brief to highlight importance of escalation to Production Leads if suitable equipment is not available prior to manufacture. | MA | 2026-01-23 | 2026-01-23 | 4 | Complete | Y | Closed CAPA File
CAPA.2026.003 | 2026-01-20 | NE | SP | DEV.2025.036 - missed yearly calibration of comark | Minor | Complete Temperature monitoring data review for affeced areas Update ES.SOP.173 - Comark Procedure Implement calibration tracking system Establish formal deputy for calibration scheduling Communicate SOP updates | SP | 2026-02-28 | 2026-02-27 | 38 | Complete | Y | Effectiveness Check File
CAPA.2026.004 | 2026-01-22 | NE | MR | Mock Inspection | Major | See CAPA for full list | MR | 2026-12-31 |  | -46044 | In-Progress |  | Open CAPA File
CAPA.2026.005/A | 2026-01-23 | GN | GN | DEV.2025.030 - no Goods out log book from Jun 25 to Oct 25 | Minor | Training Refresher for Dispatch staff via the issuing of an Awareness Brief. This will pay particular attention to data integrity and the Logbook process. “No dispatch without controlled record- emphasis on regulatory issues. | GN | 2026-02-23 | 2026-02-20 | 28 | Complete | Y | Effectiveness Check File | EC Due 20 Sep 26
CAPA.2026.005/B | 2026-01-23 | GN | GN | DEV.2025.030 - no Goods out log book from Jun 25 to Oct 25 | Minor | Add new section(s) to the Controlled Spreadsheet that identify where each logbook is, what its current status is and who should be in control of it. | GN | 2026-02-23 | 2026-02-23 | 31 | Complete | Y | Effectiveness Check File | EC Due 20 Sep 26
CAPA.2026.005/C | 2026-01-23 | GN | GN | DEV.2025.030 - no Goods out log book from Jun 25 to Oct 25 | Minor | Create a new Logbook Review Procedure to improve the issuing, correct usage and archiving of all logbooks | GN | 2026-03-31 | 2026-03-01 | 37 | Complete | Y | Effectiveness Check File | EC Due 20 Sep 26
CAPA.2026.005/D | 2026-01-23 | GN | GN | DEV.2025.030 - no Goods out log book from Jun 25 to Oct 25 | Minor | Update ES.SOP.056 and ES.SOP.220 to make sure instructions and responsibilities are clearly set with the most up to date processes. | GN | 2026-03-31 | 2026-03-20 | 56 | Complete | Y | Effectiveness Check File | EC Due 20 Sep 26
CAPA.2026.006/A | 2026-01-23 | GN | GN | DEV.2025.034 - Stability Fridge fault after maintenance | Minor | Update ES.SOP.085 to incorporate procedures for handling a temperature controlled piece of equipment that requires maintenance performing. | GN | 2026-04-30 | 2026-04-30 | 97 | Complete | Y | Closed CAPA File
CAPA.2026.006/B | 2026-01-23 | GN | GN | DEV.2025.034 - Stability Fridge fault after maintenance | Minor | Repair or decommission of Stability Fridge | GN | 2026-07-31 | 2026-07-16 | 174 | Complete | Y | Closed CAPA File
CAPA.2026.007 | 2026-01-28 | AHA | QA | DEV.2026.004 - Quetiapine Oral Suspensions Double strength supplied / REC.2026.001 | Critical | Update the BMRs for all strengths of Quetiapine Oral Suspension (QUET1, QUET2, QUET3, QUET4, QUET5, QUET7) Issue an awareness brief to all relevant staff to establish an interim control Provide initial refresher training to R&D on how to calculate API quantities for master formulas with an emphasis on the base to salt ratio verification. Provide initial refresher training to QA Pharmacist, QA Management and RPs to verify API quantity calculations prior to master formula and BMR approval. Update ES.SOP.119.V08 Provide training to QA operators Contact all customers who have received this product since 2024 | QA/ Production | 2026-02-28 | 2026-02-27 | 30 | Complete | Y | Closed CAPA File
CAPA.2026.008/A | 2026-02-27 | GN | GN | GMP.CPL.2026.002 | Minor | Update ES.SOP.013 - Batch Manufacturing Process and Supply to mention the checking of bottle cap integrity before product is completed and dispatched. | GN | 2026-04-27 | 2026-04-02 | 34 | Complete | Y | Effectiveness Check File | EC Due 02 Oct 26
CAPA.2026.008/B | 2026-02-27 | GN | GN | GMP.CPL.2026.002 | Minor | Update ES.SOP.133 – Packing Procedures to mention the checking of bottle cap integrity before product is completed and dispatched. | GN | 2026-04-27 | 2026-04-02 | 34 | Complete | Y | Effectiveness Check File | EC Due 02 Oct 26
CAPA.2026.008/C | 2026-02-27 | GN | GN | GMP.CPL.2026.002 | Minor | Update ES.SOP.191 – Line Clearance & Product Checks to mention the checking of bottle cap integrity before product is completed and dispatched. | GN | 2026-04-27 | 2026-04-02 | 34 | Complete | Y | Effectiveness Check File | EC Due 02 Oct 26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Define and implement acceptable protective measures for GMP logbooks used in manufacturing areas, including the use of protective covers, designated storage locations away from wet or high-risk areas, controlled placement during use, and protection during cleaning activities and inter-departmental transfer. | Production | 2026-05-15 | 2026-04-17 | 35 | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Introduce a revised logbook template incorporating an additional sign-off at the end of each page to confirm entries are complete, legible, recorded in real time, and that no spillage or damage to the record has occurred. In addition, implement a final documented review of completed logbooks by Production prior to transfer to QA for archiving. This requirement and updated template should be incorporated into ES.SOP.013 Batch Manufacturing Process and Supply. | GN/Production | 2026-05-15 | 2026-05-06 | 54 | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Establish controlled temporary storage requirements for completed logbooks awaiting transfer to QA to minimise risk of environmental exposure. | HK/AA | 2026-05-15 | 2026-04-17 | 35 | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Revise ES.SOP.164.V04 to include clear requirements for the protection, handling, and storage of GMP logbooks during use in manufacturing areas, inter-departmental transfer, and QA review. | HK | 2026-05-30 | 2026-05-20 | 68 | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Implement periodic QA review and monitoring of production logbooks to ensure compliance with GMP requirements, including completeness and legibility. | QA | N/A | N/A | #VALUE! | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.009 | 2026-03-13 | HK | HK | DEV.2026.001 | Minor | Provide targeted training to relevant Production and QA personnel on updated SOP requirements, including Good Documentation Practices (GDP), appropriate handling and protection of GMP documentation, and the requirement for immediate escalation through the deviation system and to management when damage or loss of GMP records is identified or suspected. | HK | 2026-05-30 | 2026-05-21 | 69 | Complete | Y | Effectiveness Check File | EC 30OCT26
CAPA.2026.010/A | 2026-03-26 | AHA | AHA | REC.2026.001, REC.2026.002 & MHRA Defective Medicines Report Centre (DMRC), A Guide to Defective Medicinal Products (Feb 2026), | Minor | Update ES.SOP.009 – Recall Procedure, if required. | AHA | 2026-05-26 | 2026-05-26 | 61 | Complete | Y | Effectiveness Check File | EC DUE 31 MAY 27
CAPA.2026.010/B | 2026-03-26 | AHA | AHA | REC.2026.001, REC.2026.002 & MHRA Defective Medicines Report Centre (DMRC), A Guide to Defective Medicinal Products (Feb 2026), | Minor | Update ES.SOP.009.F01- Product Recall Form. | AHA | 2026-05-26 | 2026-05-26 | 61 | Complete | Y | Effectiveness Check File | EC DUE 31 MAY 27
CAPA.2026.010/C | 2026-03-26 | AHA | AHA | REC.2026.001, REC.2026.002 & MHRA Defective Medicines Report Centre (DMRC), A Guide to Defective Medicinal Products (Feb 2026), | Minor | Update ES.SOP.008 - GMP Customer Complaint, if required. | AHA | 2026-05-26 | 2026-05-26 | 61 | Complete | Y | Effectiveness Check File | EC DUE 31 MAY 27
CAPA.2026.011 | 2026-04-01 | MR | MR | OOS.2026.001 | Major | Update BMR to state overage of 2% | JNB | 2026-04-30 | 2026-04-29 | 28 | Complete | Y | Effectiveness Check File
CAPA.2026.012/A | 2026-04-16 | SP | AHA | DEV.2026.008 – No temperature data log for stability samples during transit from Marfleet Analytical Services Ltd, Hull (contracted stability storage facility) to Eaststone Ltd, Bolton (manufacturer and testing site). The deviation resulted from a combination of Human Error, Procedural Gaps relating to off-site transportation requirements and pre-dispatch verification and inadequate oversight during shipment coordination. Corrective action: Pre-dispatch check list and post-dispatch check list to reinforce requirements for data logger verification. Preventative actions: Update procedure ES.SOP.218 to define • Off-site stability sample handling. • Transport conditions. • Mandatory data logger uses and verification. • Pre-dispatch checklist. • Requirements of transport provider. | Minor | Stability sample check list appended to procedure ES.SOP.218 • Pre-Dispatch • Post-Dispatch | SP | 2026-07-31 | 2026-07-24 | 99 | Complete | Y | Effectiveness Check File | EC DUE 30JUN27
CAPA.2026.012/B | 2026-04-16 | SP | AHA | DEV.2026.008 – No temperature data log for stability samples during transit from Marfleet Analytical Services Ltd, Hull (contracted stability storage facility) to Eaststone Ltd, Bolton (manufacturer and testing site). The deviation resulted from a combination of Human Error, Procedural Gaps relating to off-site transportation requirements and pre-dispatch verification and inadequate oversight during shipment coordination. Corrective action: Pre-dispatch check list and post-dispatch check list to reinforce requirements for data logger verification. Preventative actions: Update procedure ES.SOP.218 to define • Off-site stability sample handling. • Transport conditions. • Mandatory data logger uses and verification. • Pre-dispatch checklist. • Requirements of transport provider. | Minor | Update procedure ES.SOP.218 to define Off-site stability sample handling. Transport conditions. Mandatory data logger uses and verification. Pre-dispatch checklist. Requirements of transport provider. | SP | 2026-07-31 | 2026-07-24 | 99 | Complete | Y | Effectiveness Check File | EC DUE 30JUN27
CAPA.2026.013/A | 2026-04-17 | GN | AHA | DEV.2026.005 | Minor | Update ES.SOP.066 Section 7.5.5 to explicitly require that all green “Approved” labels are generated using a blank label template. | QA/QC | 2026-08-07 | 2026-08-07 | 112 | Complete |  | Effectiveness Check File | EC DUE 28FEB27
CAPA.2026.013/B | 2026-04-17 | GN | AHA | DEV.2026.005 | Minor | Revise ES.SOP.066.F03 to reposition supplier details directly below the “Material Name” field to ensure visibility during label creation and review. | QA/QC | 2026-08-07 | 2026-08-07 |  | Complete |  | Effectiveness Check File | EC DUE 28FEB27
CAPA.2026.014/A | 2026-04-17 | HK | HK | DEV.2026.006 | Minor | Revise analytical method ES.QCM.014.V04 to include explicit, step-by-step instructions for serial dilution preparation, including the requirement to use a fresh tissue when wiping the pipette at each dilution stage. | QC | 2026-07-30 | 2026-07-27 | 101 | Complete | Y | Effectiveness Check File | EC 31JAN27
CAPA.2026.014/B | 2026-04-17 | HK | HK | DEV.2026.006 | Minor | Train all relevant QC analysts on the updated version of ES.QCM.014.V04, with emphasis on correct serial dilution technique and prevention of carryover. | QC | 2026-07-30 | 2026-07-27 | 101 | Complete | Y | Effectiveness Check File
CAPA.2026.014/C | 2026-04-17 | HK | HK | DEV.2026.006 | Minor | Perform a review of other analytical methods involving low-level standard preparations to ensure sufficient detail is provided for critical dilution steps and handling techniques. | QC | 2026-07-30 | 2026-07-27 | 101 | Complete | Y | Effectiveness Check File
CAPA.2026.015/A | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Perform and document a review of available TinyTag temperature monitoring data to verify that environmental conditions remained within approved limits during the period affected by the loss of Comark electronic temperature records. | HK | 2026-05-30 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.015/B | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Revise ES.SOP.173 – Comark Software RF500A Wireless Monitoring System to include requirements for verification of continued data recording following clock changes, system restarts, reprogramming activities and other system interventions. Following approval of the revised procedure, train relevant QA personnel on the updated requirements. | SP/QA | 2026-07-30 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.015/C | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Implement a documented verification check following future BST/GMT clock changes to confirm that all affected temperature monitoring transmitters continue to record data and function as intended. | QA | 2026-07-30 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.015/D | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Review Comark system warning notifications and associated escalation requirements. Update the relevant procedures, where required, and train QA personnel on the identification, interpretation and escalation of monitoring system warning indicators to ensure monitoring system issues are identified and addressed in a timely manner. | QA | 2026-07-30 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.015/E | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Develop and implement a documented backup temperature monitoring process, including an approved form for the recording, review and management of temperature data when faults, failures or other issues affecting the functionality or data integrity of the primary monitoring system are identified. The procedure should define the use of approved backup monitoring devices (e.g. TinyTag data loggers), associated review requirements and escalation processes. Following implementation, train relevant personnel on the backup monitoring process. | QA | 2026-07-15 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.015/F | 2026-04-17 | HK | HK | DEV.2026.009 | Minor | Raise a Change Control to assess, select, qualify and implement a replacement temperature monitoring system, as the current Comark model is no longer supported by the manufacturer and ongoing servicing, replacement parts and technical support are limited. | QA | 2026-07-30 |  | -46129 | In-Progress |  | Open CAPA File
CAPA.2026.016/A | 2026-04-21 | AHA | AHA | GMP.CPL.2026.004 | Minor | Update the product list (BMR PRODUCT LIST - JAN 2025) to include pre formulated dates of manufacture to copy onto Episys when generating BMRs/Labels | AHA | 2026-05-21 | 2026-04-27 | 6 | Complete | Y | Closed CAPA File
CAPA.2026.016/B | 2026-04-21 | AHA | AHA | GMP.CPL.2026.004 | Minor | Update ES.SOP.020 - Episys Document Generation & Usage to incorporate the new procedure of only copying the formulated dates onto the Episys date field. | AHA | 2026-05-21 | 2026-05-06 | 15 | Complete | Y | Closed CAPA File
CAPA.2026.017/A | 2026-04-27 | MR | MR | OOS.2026.003 - Levomet 6mg high assay | Major | Update the sampling plan document to allow further monitoring of homogeneity | QC |  |  | -46139 | In-Progress |  | Open CAPA File
CAPA.2026.017/B | 2026-04-27 | MR | MR | OOS.2026.003 - Levomet 6mg high assay | Major | Revalidation of Levomet with new mixer | IP |  |  | -46139 | In-Progress |  | Open CAPA File
CAPA.2026.018 | 2026-05-11 | NAD | MA | DEV.2026.013 - 4 point scale instruction not followed | Minor | Issue the awareness brief Update ES.SOP.018 | MA | 2026-06-25 | 2026-06-25 | 45 | Complete | Y | Effectiveness Check File
CAPA.2026.019 | 2026-05-12 | GN | MA | DEV.2026.015 | Minor | The CAPA will be in relation to DEV.2026.015 in which doxycycline suspension was rejected due to excessive foaming when shaken. The CAPA actions will address any formulation issues, mixing parameters and investigate any similar products | MA | 2026-07-31 |  | -46154 | In-Progress |  | Open CAPA File
CAPA.2026.020/A | 2026-05-13 | HK | MA | Raw material management audit | Major | Update the PRS for all APIs to include an assessment of the material manufacturer, documentation and testing to determine which APIs are high risk and require additional oversight. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/B | 2026-05-13 | HK | MA | Raw material management audit | Major | Update ES.SOP.066 to detail how an API is classified as high-risk as per the updated PRS. Also, define criteria requiring audits, GMP inspection report review, or alternative assurance measures where physical audits are not practical to ensure that higher-risk manufacturers and supply chains are appropriately identified, risk-rated, and escalated for additional oversight where required. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/C | 2026-05-13 | HK | MA | Raw material management audit | Major | Train all relevant QC/QA staff on the new PRS and risk assessment process | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/D | 2026-05-13 | HK | MA | Raw material management audit | Major | Complete retrospective risk assessments for all approved APIs using the revised PRS and identify any materials requiring enhanced testing, supplier assurance activities or audit consideration. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/E | 2026-05-13 | HK | MA | Raw material management audit | Major | Establish a periodic verification testing program for selected APIs identified as high risk through the updated PRS process. This may include testing APIs from new manufacturers, higher-risk supply chains, third-country manufacturers, or periodic rotational verification testing. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/F | 2026-05-13 | HK | MA | Raw material management audit | Major | Update ES.SOP.066 to formally justify when reliance on supplier CoAs is acceptable and define the criteria and rationale for reduced testing approaches used within Eaststone. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/G | 2026-05-13 | HK | MA | Raw material management audit | Major | Create a formal excipient risk assessment template to categorise excipients based on relevant risk factors4 | QA/QC | 2026-07-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/H | 2026-05-13 | HK | MA | Raw material management audit | Major | Update ES.SOP.066 to define when additional assurance measures are required. This should be based on the result of the excipient risk assessment. | QA/QC | 2026-08-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/I | 2026-05-13 | HK | MA | Raw material management audit | Major | Complete excipient risk assessments for all approved excipients and assign risk classifications in accordance with the approved methodology. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/J | 2026-05-13 | HK | MA | Raw material management audit | Major | A risk assessment should be implemented for higher-risk excipients associated with historical DEG/EG contamination incidents, such as glycerol, propylene glycol, macrogols below molecular weight 1000, and relevant polyol-based excipients. The assessment should consider factors including supply chain complexity, use of brokers or repackers, intended product use (particularly oral and paediatric formulations), supplier qualification status, existing supplier controls, and current incoming goods verification activities. The purpose should be to evaluate the current control strategy and define any additional controls required (e.g. additional testing). | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/K | 2026-05-13 | HK | MA | Raw material management audit | Major | A periodic verification testing program should be implemented for high-risk excipients to provide independent confirmation of supplier results. This does not necessarily need to be performed on every batch or container. A risk-based approach may be adopted, such as testing the first batch from a new supplier or manufacturer, annual verification testing, testing at defined batch intervals, or testing triggered by quality concerns or supply chain changes. Testing should include the relevant Ph. Eur. DEG/EG limit test performed by a suitably qualified laboratory. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/L | 2026-05-13 | HK | MA | Raw material management audit | Major | Conduct a risk assessment to define the appropriate use and limitations of FTIR, Raman, and TruScan testing for raw material verification. The assessment should evaluate the suitability of these techniques for identity confirmation and whether they are appropriate for detecting impurities, such as DEG/EG. Where these techniques are not validated for impurity detection, the risk assessment should define what additional controls are required such as, supplier CoA review, periodic independent verification, or outsourced testing where required. | QA/QC | 2026-08-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/M | 2026-05-13 | HK | MA | Raw material management audit | Major | ES.SOP.066 should be updated to clearly distinguish between identity testing and impurity/contaminant testing requirements for higher-risk excipients associated with DEG/EG contamination risk. Based on the results of the risk assessment the procedure should define the purpose, capabilities, and limitations of FTIR, Raman, and TruScan testing and define which tests are considered appropriate for such contaminants. | QA/QC | 2026-08-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.020/N | 2026-05-13 | HK | MA | Raw material management audit | Major | The relevant PRSs should be updated to formally identify these materials and document the controls required to manage this risk associated with DEG/EG contamination risk. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.021/A | 2026-05-13 | HK | MA | Raw material management audit | Major | Develop and implement a Raw Material Shelf-Life Assignment Risk Assessment Form to provide a documented scientific rationale for assignment of internal expiry or retest dates. The assessment should consider, where applicable: • Manufacturer expiry date • Whether the material remains in the original unopened manufacturer packaging. • Frequency of opening and use. • Repackaging activities. • Exposure to air, moisture, oxygen or humidity. • Temperature sensitivity. • Photosensitivity. • Hygroscopicity. • Volatility. • Oxidation potential. • Microbiological susceptibility. • Physical stability considerations (e.g. crystallisation, caking, viscosity changes). • Chemical stability considerations. • Storage conditions. • Packaging type and closure integrity. • Available stability data, literature or pharmacopoeial information. • Historical use and quality performance within Eaststone. The assessment should define whether the manufacturer's assigned shelf life can be retained, whether a reduced shelf life is required, or whether additional justification is necessary. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.021/B | 2026-05-13 | HK | MA | Raw material management audit | Major | Update ES.SOP.066 to define the process for assignment of internal expiry and retest dates. The procedure should require documented justification for any deviation from the manufacturer's assigned expiry or retest period and prohibit use of a default fixed shelf-life assignment without supporting rationale. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.021/C | 2026-05-13 | HK | MA | Raw material management audit | Major | Once material risk assessment has been complete and a new expiry has been assigned, update all relevant material documentation and labels to that the ensure new expiry is assigned. | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.021/D | 2026-05-13 | HK | MA | Raw material management audit | Major | Perform a retrospective review of all approved APIs and excipients currently assigned a default two-year shelf life. Complete the newly implemented Raw Material Shelf-Life Assignment Risk Assessment for each material category and determine whether existing assigned expiry or retest dates remain appropriate. | QA/R&D | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.022 | 2026-05-13 | HK | MA | Raw material management audit | Minor | Raw material Audit minor actions (all listed in CAPA.2026.022) | QA/QC | 2026-12-30 |  | -46155 | In-Progress |  | Open CAPA File
CAPA.2026.023/A | 2026-05-19 | AHA | AHA | DEV.2026.011 | Minor | Update ES.SOP.218 – Stability Procedure and Guideline to formally incorporate a requirement for QA review and approval of stability data at each scheduled testing timepoint. The SOP update should also clearly define responsibilities for both QC and QA in relation to interim stability data review and oversight. on the revised process following document approval and implementation. | AHA | 2026-07-19 | 2026-07-15 | 57 | Complete | Y | Effectiveness Check File | EC DUE 16JAN27
CAPA.2026.023/B | 2026-05-19 | AHA | AHA | DEV.2026.011 | Minor | Formally notify all QC personnel of new stability data review requirements | AHA | 2026-07-19 | 2026-07-15 | 57 | Complete | Y | Effectiveness Check File | EC DUE 16JAN27
CAPA.2026.024/A | 2026-05-19 | MR | HK | DEV.2026.012 & DEV.2026.016 | Minor | Replace the identified drive motor and complete the necessary repair of the VH Mixer to return the equipment to a serviceable condition. | Production | 2026-06-30 | 2026-05-19 | 0 | Complete | Y | Effectiveness Check File
CAPA.2026.024/B | 2026-05-19 | MR | HK | DEV.2026.012 & DEV.2026.016 | Minor | Perform and document a trial run following completion of the repair to verify the VH Mixer operates correctly and is suitable for its intended use prior to release for routine manufacturing. | Production | 2026-06-30 | 2026-05-19 |  | Complete | Y | Effectiveness Check File
CAPA.2026.025 | 2026-05-29 | HK | HK | Supplier qualification audit | [5 empty] | -46171 | In-Progress |  | E-Copy
CAPA.2026.026 | 2026-06-26 | NAD | NAD | DEV.2026.020 - Tinytag actions | Major | See CAPA for full list | NAD | 2026-08-31 |  | -46199 | In-Progress |  | Open CAPA File
CAPA.2026.027 | 2026-07-05 | MR | MR | DEV.2026.021 - Use of expired Api midazolam in midabuc | Critical | See CAPA for full list | MR | 2026-09-30 |  | -46208 | In-Progress |  | Open CAPA File
CAPA.2026.028/A | 2026-07-05 | AHA | AHA | DEV.2026.017 | Minor | Reinstate and a controlled Approved Fridge Line Product List within ES.SOP.139. | AHA | 2026-08-12 | 2026-08-12 |  | Complete | Y | Effectiveness Check File | EC DUE 12 NOV 26
CAPA.2026.028/B | 2026-07-05 | AHA | AHA | DEV.2026.017 | Minor | Revise ES.SOP.083 to require verification of transportation requirements against the approved fridge line list before generating courier labels. | AHA | 2026-08-12 | 2026-08-12 |  | Complete | Y | Effectiveness Check File | EC DUE 12 NOV 26
CAPA.2026.028/C | 2026-07-05 | AHA | AHA | DEV.2026.017 | Minor | Retrain Dispatch personnel on the revised process and reinforce the requirement to verify transportation requirements before label generation. | AHA | 2026-08-12 | 2026-08-12 | 38 | Complete | Y | Effectiveness Check File | EC DUE 12 NOV 26
CAPA.2026.029 | 2026-07-29 | MUA | MUA | OOS.2026.004 - High assay results in Levomet Tablets | Major | Process Validation Specification and Worksheet updates for all applicable products LOD implementation for MCC and SSG | JNB | 2026-12-31 |  | -46232 | In-Progress |  | Open CAPA File
CAPA.2026.030 | 2026-07-29 | MA | MA | DEV.2026.025 | Minor |  | MA |  |  | -46232 | In-Progress |  | E-Copy
CAPA.2026.031/A | 2026-07-30 | HK | HK | DEV.2026.023 | Minor | Arrange for Howorth Air Technology Limited to complete the recommended remedial work detailed in Appendix 3 of DEV.2026.023. | Production | 2026-09-30 | 2026-08-05 | 6 | Complete | Y | Effectiveness Check File | EC 08MAR26
CAPA.2026.031/B | 2026-07-30 | HK | HK | DEV.2026.023 | Minor | Obtain and review written confirmation from Howorth Air Technology Limited that the remedial work has been completed satisfactorily. | Production | 2026-09-30 | 2026-08-05 |  | Complete | Y | Effectiveness Check File
CAPA.2026.032/A | 2026-08-07 | NAD | NAD | DEV.2026.024 | Major | Issue an interim Awareness Brief instructing Production technicians not to rush tasks and to seek support where required. Trainers must directly observe trainees during critical filling activities until competency is demonstrated. These requirements will be formalised in the revised ES.SOP.013, and completion of the brief must be documented. | AA | 2026-08-31 |  | -46241 | In-Progress |  | Open CAPA File
CAPA.2026.032/B | 2026-08-07 | NAD | NAD | DEV.2026.024 | Major | Revise ES.SOP.013 – Batch Manufacturing Process & Supply to incorporate the approved findings from the practical trial and the approved findings from DEV.2026.024. | WB/AA | 2026-08-31 |  | -46241 | In-Progress |  | Open CAPA File
CAPA.2026.032/C | 2026-08-07 | NAD | NAD | DEV.2026.024 | Major | Review and update ES.COM.056 to require the following information to be recorded for each bottle size or presentation. Review ES.COM.058 – Stock Batches (90 Days Shelf Life) and implement any corresponding changes required to ensure that the same filling, volume-check and actual-overage controls are applied to 90-day stock batches. If no update is required, the review and justification must be documented. | WB/AA | 2026-09-30 |  | -46241 | In-Progress |  | Open CAPA File
CAPA.2026.032/D | 2026-08-07 | NAD | NAD | DEV.2026.024 | Major | Destroy the twelve quarantined 50ml bottles in accordance with the approved disposal procedure. Retain evidence of destruction with DEV.2026.024. | NAD | 2026-08-31 |  | -46241 | In-Progress |  | Open CAPA File
CAPA.2026.033/A | 2026-08-10 | AHA | AHA | GMP.CPL.2026.006 | Minor | Conduct a site-wide review of all primary packaging container types used for finished product packaging to identify and document the different packaging types in use and ensure they are labelled with the finished product labelling when manufacturing. | AHA | 2026-09-10 |  | -46244 | In-Progress |  | Open CAPA File
CAPA.2026.033/B | 2026-08-10 | AHA | AHA | GMP.CPL.2026.006 | Minor | Revise ES.SOP.042 – Finished Product Labels to explicitly define the requirement for finished product labelling of all primary packaging components, including less frequently used primary packaging such as suppository moulds, creams, ointments and gels. | AHA | 2026-09-10 |  | -46244 | In-Progress |  | Open CAPA File
CAPA.2026.034/A | 2026-08-26 | AHA | AHA | CMPS.2026.001 | Minor | Update ES.SOP.066 – Raw Materials – Ordering, Receipt, QC Release & Storage to include an explicit requirement for the visual examination of samples for foreign particulate matter, where applicable. | AHA | 2026-10-02 |  | -46260 | In-Progress |  | E-Copy
CAPA.2026.034/B | 2026-08-26 | AHA | AHA | CMPS.2026.001 | Minor | Update ES.SOP.160 – Sampling of Finished Products to include an explicit requirement for the visual examination of samples for foreign particulate matter, where applicable. | AHA | 2026-10-02 |  | -46260 | In-Progress |  | E-Copy
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0