## Change Controls
Spreadsheet no: ES.CSV.016 CHANGE CONTROLS Spreadsheet Owner: Omair Sattar Ref. SOP: ES.SOP.052 |  |  |  | QMS DATA EFFECTIVENESS CHECKS Version 1.0
CC Reference | Date CC Raised | Responsible Person | Target date | Effectiveness check action(s) | Status | Wet Ink Copy Filed (Y/N) | Date Closed | Location | Comments
CC.2026.012 | 2026-02-03 | GN | 2026-06-10 | Check to see if we have any rejected batches or deviaitons for the new formulation. | Complete | Y | 2026-06-10 | Closed CC File
CC.2026.013 | 2026-02-04 | GN | 2026-07-25 | Check to see if we have any rejected batches or deviaitons for the new formulation. | Complete | Y | 2026-07-24 | Closed CC File
CC.2026.017 | 2026-02-09 | SSP | 2026-09-06 | Check to see if the new clinical needs established on the BMR has been selected approriately during order generation. | In-Progress | Y |  | Effectiveness Check File
CC.2026.023 | 2026-02-23 | MR | 2026-04-30 | Reintroduction of MEXI3 with 12 months shelf life | Complete | Y | 2026-04-30 | Closed CC File
CC.2026.024 | 2026-02-23 | HK | 2026-06-30 | Check to see if any issues have arise with SBS chambeer post maintenance and calibration | In-Progress | Y |  | Effectiveness Check File
CC.2026.029 | 2026-03-09 | AHA | 2026-10-15 | Assess ease of use of new container, if weighing discrepancies have occurred, any deviations have occurred due to the new container | In-Progress | Y |  | Effectiveness Check File
CC.2026.030 | 2026-03-10 | GN | 2026-10-09 | Check to see if updated formulations have caused any rejected batches or deviations | In-Progress | Y |  | Effectiveness Check File
CC.2026.022 | 2006-02-23 | HK | 2026-11-30 | Review future midazolam micro results to confirm no issues with validation and results are as expected | In-Progress | Y |  | Effectiveness Check File
CC.2026.064 | 2026-06-15 | AHA | 2027-01-01 | Check to see if the powder has resolved supply issues based on batches subsequently manufactured. Check to see if orders received have been completed. | In-Progress | Y |  | Effectiveness Check File
CC.2026.004 | 2026-01-08 | AHA | 2026-12-31 | Check to see if new formulation has created any issues rejected batches and / or deviations | In-Progress | y |  | Effectiveness Check File
CC.2026.050 | 2026-05-05 | AHA | 2026-11-07 | Check to see if introduction of replacement material is suitable and effective via rejected batch + deviation monitoring | In-Progress | y |  | Effectiveness Check File
CC.2026.058 | 2026-05-20 | SSP | 2026-12-17 | Check to see if new process and log book are being utilised and checks are being conducted in timely manner. | In-Progress | Y |  | Effectiveness Check File
CC.2026.037 | 2026-04-08 | SSP | 2026-12-31 | Check to see appropriate clinical need has been assigned on batches generated. | In-Progress | y |  | Effectiveness Check File
CC.2026.036 | 2026-04-08 | SSP | 2026-12-30 | Check to see appropriate clinical need has been assigned on batches generated. | In-Progress | y |  | Effectiveness Check File
CC.2026.057 | 2026-05-20 | SSP | 2026-12-30 | Check to see if correct clinical needa are being applied to generated batches of this product. | In-Progress | y |  | Effectiveness Check File
CC.2026.067 | 2026-06-23 | SSP | 2027-02-27 | Check to see if correct clinical needa are being applied to generated batches of this product. | In-Progress | Y |  | Effectiveness Check File
CC.2026.014 | 2026-02-05 | MR | 2026-11-30 | Review log book reviews, review findings and see if deviations have been raised appropriately | In-Progress | Y |  | Effectiveness Check File

## CAPAs
Spreadsheet no: ES.CSV.016 CAPAs Spreadsheet Owner: Omair Sattar Ref. SOP: ES.SOP.044 |  |  |  | QMS DATA EFFECTIVENESS CHECKS Version 1.0
CAPA Reference | Date CAPA Raised | Responsible Person | Target date | Effectiveness check action(s) | Status | Wet Ink Copy Filed (Y/N) | Date Closed | Location | Comments
CAPA.2026.001 | 2026-01-02 | SSP | 2026-08-04 | Check to see if we have received and complaints raised and deviations or ejected batches because of foaming of this product or any other product | Complete | Y | 2026-08-04 | Closed CAPA File
CAPA.2026.002 | 2026-01-19 | MA | 2026-05-30 | Review deviation and rejected batch log to identify any recurring issues with material mixups, specially where the root cause is identified as human error or procedure is defficient | In-Progress | Y | 2026-05-29 | Closed CAPA File
CAPA.2026.003 | 2026-01-20 | MR | 2027-01-01 | Check to see is calibration has been planned and executed in a timely manner | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.005 | 2026-01-23 | GN | 2026-09-20 | Check to see if any furhter data integrity issues have occurred and if Dispatch have shown any gap in GMP awareness | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.007 | 2026-02-02 | MR | 2026-05-27 | Ensure no repeat occurrences review staff competency completions | In-Progress | Y | 2026-05-26 | Closed CAPA File
CAPA.2026.008 | 2026-02-27 | GN | 2026-10-02 | Check to see if repeat incidents occur and can be contributed to not following updated SOPs | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.016 | 2026-04-21 | AHA | 2026-09-06 | Check to see if the same type of deviation/GMP complaint has occurred since implementation. Check to see if the new process is being adhered to by the BMR generator and if the formulas work. | Complete | Y | 2026-09-04 | Closed CAPA File
CAPA.2026.011 | 2026-04-01 | MR | 2027-07-31 | Review effectiveness of this change in overage amount by reviewing subsequent batches, also review status of process validation. Review subsequent OOS for this product | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.009 | 2026-03-13 | HK | 2026-10-30 |  | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.010 | 2026-03-26 | AHA | 2027-05-31 | Perform mock recall utilising updated process | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.018 | 2026-05-11 | MA | 2026-10-31 | Check to see if newly updated procedure has prevented this type of deviation. Review deviations or rejected batches | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.023 | 2026-05-19 | AHA | 2027-01-16 | Check to see if updated SOP is being followed and QA independent review is being performed | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.012 | 2026-04-16 | AHA | 2027-06-30 | Check to see if new process is being utilised correctly and has prevented recurrence of this deviation | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.014 | 2026-04-17 | HK | 2027-01-31 | Check to see if results obtained are as expected and elevated peaks do not occur with addition of added technique. | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.024 | 2026-05-19 | HK | 2026-09-21 | CHECK TO SEE IF EQUIPMENT RESENTS ANY FURTHER ISSUES | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.013 | 2026-04-17 | AHA | 2027-02-28 | Check to see if any incorrect supplier has been assigned to a raw material/excipient label and for repaeat deviations. Check to see if updated form format has resloved the issue. | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.028 | 2026-07-05 | AHA | 2026-11-12 | Check to see if repeat deviations occur and if new form with list of fridge line goods is being correctly utilised | In-Progress | Y |  | Effectiveness Check File
CAPA.2026.023 | 2026-07-30 | HK | 2026-03-08 | Check if there is no water leak in plant room | In-Progress | Y |  | Effectiveness Check File

## Deviations
Spreadsheet no: ES.CSV.016 DEVIATIONS Spreadsheet Owner: Omair Sattar Ref. SOP: ES.SOP.015 |  |  |  | QMS DATA EFFECTIVENESS CHECKS Version 1.0
Deviation Reference | Date Deviation Raised | Responsible Person | Target date | Effectiveness check action(s) | Status | Wet Ink Copy Filed (Y/N) | Date Closed | Location | Comments